## Active Listening Panel Timeline
Active Listening Panel Timeline
Insert 'X' in timeline cell and will mark as blue.
| [insert month-year] |  |  |  | 2021-07-01 |  |  |  | 2021-08-01 |  |  |  |  | 2021-09-01 |  |  |  | 2021-10-01 |  |  |  | 2021-11-01 |  |  |  |  | 2021-12-01
PROJECT STAGES | insert week beginning | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27
STAGE 1 - ALP SCOPING | bar: 14
Identify/consider topic (Use ALP Framework*, and Scoping Document*) | bar: 21 to 28
Host internal meetings with internal sponsors to discuss needs, process, outputs and timelines | bar: 2021-07-01 5 to 2021-07-01 12
Conduct secondary intelligence gathering (desk research) to identify key stakeholders and known factors that may impact the ALPs | bar: 2021-07-01 12
STAGE 2 - PLANNING
Finalise question set in collaboration with project sponsor and project team, and input to Facilitation Guide and Question Set* document | bar: 2021-07-01 19 to 2021-07-01 26
Create documents that meet project team needs - e.g. invitation email templates, evaluation questions, briefing documents to share with participants prior to attendance, etc. | bar: 2021-07-01 26
Finalise list of stakeholders to be invited and utilise Attendance Pipeline* document to manage invitations | bar: 2021-07-01 26 to 2021-08-01 2
Finalise Scoping Document* and Facilitation Guide and Question Set* | bar: 2021-08-01 9 to 2021-08-01 16
STAGE 3 - RECRUITMENT
Initiate contact with identified stakeholders to discuss ALP invitation (build relationship): phone | bar: 2021-08-01 23
Follow up invitation in writing (include any pre-attendance content) | bar: 2021-08-01 30
Update ALP Attendance Pipeline* | bar: 2021-08-01 30
Send out appropriate diary marker (e.g. video-conference link) | bar: 2021-09-01 6
Confirm attendance numbers and update Attendance Pipeline* | bar: 2021-09-01 6 to 2021-09-01 13
STAGE 4 - HOSTING AND FACILITATING
Host and facilitatite ALPs | bar: 2021-09-01 20 to 2021-10-01 25
Send 'thank you' email and continue to build relationships | bar: 2021-11-01 1
STAGE 5 - REPORTING
Draft report, conduct due dilligence meeting with both facilitator and note taker present to confirm intelligence themes noted, finalise and issue ALP Internal Intelligence Briefing(s) in line with agreed distribution (refer to Scoping Document*) | bar: 2021-09-01 20 to 2021-11-01 8
STAGE 6 - LESSONS LEARNED
Conduct/host lesson learned meeting with project team to discuss the ALP delivery, the next steps for the project in light of emerging intelligence and plan future engagement activity with participants. Note: Follow up with all participants within project engagement schedule to continue to build relationship capital and positive relationships. | bar: 2021-11-01 29 to 2021-12-01 6
* Template documents available in the ALP Toolkit